## E and D Summary
| 2024 Measure E | 2014 Measure D | Notes | Cost | Notes
New Buildings
Preschool |  | 2400000
Design Lab |  | 1600000
Sellman |  | 7750000 | Measure D: Includes $150k addition for AC in 2017 after the building was built
Replace Kinder/TK | 13416657.696
Total New Buildings | 13416657.696 | 11750000
Building Upgrades
Roofing | 1158240 | 275000 | Measure D: Repair of dry rot damage wood framing and sheathing. Re-roofing with asphalt shingles in selected areas. Installation of new ridge vent and limited replacement of flashing & Gutters at Classroom 30-35.
Roofing/Drainage & Infrastructure Upgrade Project | 1338260 | 1700000 | Measure E: Paving main hard court, Kinder, Parking Lot; Measure D: At 2nd and 3rd grade building: Installed new storm drain piping (Classroom 10 and Electrical Rooms) Replace concrete paving as required for new work. At Kindergarten Room 14 and 4th grade wing: Remove three existing trees, install new storm drain and piping (Classrooms 14, 17, & 18 & small section between classrooms 16 & 17) Install new concrete paving slope to drain. At Breezeway between 3rd grade classrooms and Kindergarten Room 14: Remove tree, install new storm drain piping for existing downspout, replace concrete as required for new work. Repair existing water piping Southwest of Room 38 offices and North of 2nd and 3rd grade building. Replace sewer line South of 2nd & 3rd Grade Classrooms.
New HVAC | 769240 |  | Measure D: Looking at the approved DSA drawings, this project was not done. Pricing efforts were provided through the Facilities Condition Assessment Tool. Approx $600k
Exterior Upgrades | 2247490 |  | Measure E: Lighting, exterior wall finish, doors, window coverings, windows
Interior Upgrades | 1937730 |  | Measure E: carpet, painting, etc
Install solar panels and batteries
Remodel Bathrooms by Lockers
Total Building Upgrades | 7450960 | 1975000
Grounds
Athletic Fields | 3120000 |  | Measure E: new artificial turf, shade structures, new play structures
Creek Stabilization | 3067200
Amphitheater Renovation Project | 2200000 | 120000 | Painting of the benches, Electrical to include new PVC conduits for speakers, new electrical panel behind stage, (1) one new B-K Lighting Power/Sound bollards.
Natural Turf Project | 350000 | 200000 | Removal and replace Soccer Field
Tree Plan/Grounds Beautification
Total Grounds | 8737200 | 320000
Safety/Security/Technology
Safety and Security | 1900000 | 600000 | Measure E: security cameras, new fire alarm; Measure D: Traffic bollards at various locations, LED exterior lighting on Building Classroom 21-24, Security and Fencing at Pre-school, Hardcourt Re-surfacing, Exterior signage light at School Office Building, Convert school door hardware to classroom security function, replace 28 ND series leversets, convert or replace 33 mortise locks, convert 40 Corbin panic devices to Von Duprin panic devices with cylinder dogging function at Kinder/Pre-K classrooms, security classrooms.
Technology Upgrades | 760000 | 300000 | Measure E: Cosnolidate tech equipment to one room, new P/A bell system, sound system; Measure D: Replacement of the phone, clock, intercom, PA systems
Total Safety/Security/Technology | 2660000 | 900000
Misc./Other
Renovation Contingencies | 1501172
Renovation Soft Costs | 4803750.4
Renovation Inflation | 3410662.784
Total Misc./Other | 9715585.184
Grand Total | 41980402.88 | 14945000

## Priorities Summary
|  | Only includes CPM #s | Includes CPM & Estimates
|  | 2024 Measure E Total Projects | 2024 Projects | 2027 Projects | 2030 Projects
New Buildings
Replace Kinder/TK |  | 13416657.696 | 13416657.696
Total New Buildings |  | 13416657.696 | 13416657.696 | 0 | 0
Building Upgrades
Exterior Upgrades
| Roofing | 1158240 | 324270 | 548600
| New HVAC (1/3 of total every 3 years) | 769240 | 256413.3333 | 256413.3333 | 256413.3333
| Drinking Fountains |  | 20000
| Exterior Doors |  | 318080 | 0 | 0
| Windows |  | 121970 | 75120 | 0
| Window Coverings |  | 203500
Exterior Wall Finish
| Fascia |  | 25000 | 45000 | 0
Columns
| Exterior Lighting |  |  |  | 461460
MS Exterior Light Fixtures
Interior Upgrades
| Flooring |  | 150000 | 150000 | 200000
| Painting |  |  | 396410
| Counter Tops |  | 111000 | 50000 | 100000
| Partitions Rooms 10-13 |  |  | 54530
| Wall Finish - Vinyl Covered Tackboard |  |  | 200000
| Remodel Kids' Bathrooms by Lockers & CR 10-13 |  | 240000
Total Building Upgrades |  |  | 1770233.3333 | 1776073.3333 | 1017873.3333
Grounds/Infrastructure
Athletic Upgrades
| Natural Tuf/Kinder Field |  |  | 350000
| Artificial Turf |  |  | 1800000
| Shade Structures |  |  | 500000
| Play Structures |  |  | 450000
Fencing |  |  | 45000
Paving |  |  | 296430 |  | 250000
Creek Stabilization |  | 3067200 |  | 3067200
Amphitheater Renovation Project |  | 2200000 |  | 2200000
Drains in breezeway btw 38 and 39 (5 or 10 years) |  |  |  |  | 60000
6 New Man Holes - CPM in tandem w new K building
Water Line to Tennis Court
Tree Plan/Grounds Beautification/Landscaping
Total Grounds |  | 5267200 | 341430 | 8367200 | 310000
Safety/Security/Technology
Install solar panels and batteries
Fire Alarm Replacement |  | 1100000 | 1100000
Technology Upgrades
| Tech Hub Room 15 | 450000 | 450000
| Tech Upgrades to Wildcats | 70000 | 70000
| Sound System Sellman | 80000 | 80000
| New PA/Bell System | 300000 | 300000
Total Safety/Security/Technology |  | 2000000 | 2000000 | 0 | 0
Misc./Other
Renovation Contingencies |  | 1501172 | 411166.3333 | 707607.3333
Renovation Soft Costs |  | 4803750.4 | 1315732.2667 | 2264343.4667
| Renovation Subtotal | 13572122.4 | 5838561.9333 | 13115224.1333 | 1327873.3333
| 8% inflation first year | 1085769.792 | 467084.9547 | 1049217.9307 | 106229.8667
| 4% inflation second year | 586315.6877 | 252225.8755 | 566577.6826 | 57364.128
| 4% inflation third year | 609768.3152 | 262314.9105 | 589240.7899 | 59658.6931
Total Inflation |  | 2281853.7949 | 981625.7407 | 2205036.4031 | 223252.6878
Grand Total |  | 29270633.8909 | 20236845.3701 | 15320260.5364 | 1551126.0211
Note on H37: Estimate for resealing by Fac Group
Note on H40: Jenny estimate

## Martinez addtl
Roofing
| Classrooms | Cost Estimate | Timing
| 10 | Need | Need | Leak - is this mechanical screen issue - CPM is working on this
| 11 | Need | Need | Leak
| 15 | Need | Need | Leak
| Classrooms 26-29 (overhang?) | Need | Need | Leak
| Classroom 23 | Need | Need | Roof Exhaust
Interior Building
| Ballast (Electrical) | Need | Need
| Switch to LED lights - Interior | Need | Need
| Classroom 23 (electrical) | Need | Need | Floor outlets
| Classroom 24 (electrical) | Need | Need | Floor outlets
| Men's Toilet Room classroom 10-13 | 2500 |  | Counter and sinks replaced
| Women's Toilet Room classroom 10-13 | 2500 |  | Counter and sinks replaced
| Boy's Toilet Room classroom 10-13 | N/A - Remodel |  | Lights fixed
| Girl's Toilet Room classroom 10-13 | N/A - Remodel |  | Lights fixed
| Boy's Toilet Room classroom 10-13 | N/A - Remodel |  | Electrical pipes covered
| Girl's Toilet Room classroom 10-13 | N/A - Remodel |  | Electrical pipes covered
| Roller gate area (classrooms 23-25) | Need | Need | Hallway lights
| Roller gate area (classrooms 23-25) | Need | Need | Both Roller gates
| Boy's Toilet Room classroom 23-25 | 60000 |  | Remodeled - CPM
| Girl's Toilet Room classroom 23-25 | 60000 |  | Remodeled - CPM
| Boy's Toilet Room classroom 10-13 | 60000 |  | Remodeled - CPM
| Girl's Toilet Room classroom 10-13 | 60000 |  | Remodeled - CPM
Sinks (is that included in CPM estimate of counter?)
| Room Islands (teachers' desks) classrooms 10-13 | Need | Need | Removed or repaired
| Room Islands (teachers' desks) classrooms 16-17 | Need | Need
| Classroom 10-13 | 37000 |  | Window Coverings/Blinds
| Classroom 15-18 | 37000 |  | Window Coverings/Blinds
| Classrooms 26-35 | 92500 |  | Window Coverings/Blinds
| Library | 37000 |  | Window Coverings/Blinds
Exterior
| Replace light fixtures | Need | Need | Middle School court yard
| Classroom 38B, 38C, 38D | Need | Need | Drains in breezeway - was this worked on in Measure D
| Umbrellas | Need | Need | May be resolved with shade structure
| Classroom 19 | 0 |  | Leak in front of Room 19 - XL to fix?
| Columns (breezeway from Admin to Room 21) | Need | Need | Repair and paint
Site
| Water Line to tennis court | 600000 |  | May cap it or run a line from preschool - Michelle to contact town
| 6 more Sewer Man Holes | Need | Need
| Clean out and organize storage | Need | Summer 24 | Store umbrellas/lawn mowers/turf field cleaner/garden tools
| Tree Plan/Grounds beautification |  |  | Hire Landscape architect
Athletic
| McCovey Field | 0 | Need | Metal roof in dugout and pipe on the bottom of fencing (Little League pays?)

## Itemized List update
Roofing Repair work |  |  |  | Filtered Total: |  |  |  |  | 1158240 |  |  |  |  | Original Master Plan Itemized list Breakdown |  | 2023-11-28 | 2785000
Building ID | Building Description | Room Description | Item | Notes (Second Assessment) | Assessed Condition | Remaining Years At Time of Assessment | Year of Assessment | Anticipated Replacement Date | Estimated Cost (Rounded) | Martinez yes? | Year Built | Year of Most Recent Renovation | Facilities Committee Planned Replacement Date | Revised Master Plan Itemized List Breakdown |  | 2024-02-08 | 1158240
X | X | X | X |  | X | X | X | X | X
AA | Classrooms 6-8 | Exterior | Roof |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 114900 |  | 2006 | 2006 | 2027 | In 3 years
AA | Classrooms 6-8 | Exterior | Gutters |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5650 |  | 2006 | 2006 | 2027
B | Classrooms 10-13 | Exterior | Roof | Canopy is bad. Roof is ok. | 00 - Critical - Replace Now | 0 | 2022 | Now | 174040 |  | 1969? | 2015
D | Classrooms Kindergarten | Exterior | Roof | Per the Roofing report | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 0 |  | 1969 | 2015 | New Build
DD | Music Classrooms 36 &37 | Exterior | Roof |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 169520 |  | 2006 | 2006 | 2027
DD | Music Classrooms 36 &37 | Exterior | Gutters |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3920 |  | 2006 | 2006 | 2027
E | Classrooms 15-19 | Exterior | Gutters |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 6270 |  | 1969? | 2015
F | Classrooms 26-29 | Exterior | Roof | Per the Roofing report | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 105060 |  | 1969? | 2015
FF | Classrooms 9, 14, & 20 | Exterior | Roof | Per the Roofing report | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 151100 |  | Classrooms 14, 20 built in '06 | 2006 | 2027
FF | Classrooms 9, 14, & 20 | Exterior | Gutters |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5210 |  | Classrooms 14, 20 built in '06 | 2006 | 2027
G | Community Gym | Exterior | Roof | Per the Roofing report | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 308810 | yes | 2002 | 2002 | 2024
G | Community Gym | Exterior | Gutters |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9500 | yes | 2002 | 2002 | 2024
G | Community Gym | Exterior | Roof Drains | Per the Roofing report | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5960 | yes | 2002 | 2002 | 2024
GG | Classrooms 21 & 22 | Exterior | Roof | Canopy only. | 00 - Critical - Replace Now | 0 | 2022 | Now | 94120 |  | 2006 | 2006 | 2027
GG | Classrooms 21 & 22 | Exterior | Gutters |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4180 |  | 2006 | 2006 | 2027
HVAC |  |  |  | Filtered Total: |  |  |  |  | 769240 |  |  |  |  | Original Master Plan Itemized list Breakdown |  | 2023-11-28 | 1000012
Building ID | Building Description | Room Description | Item | Notes (Second Assessment) | Assessed Condition | Remaining Years At Time of Assessment | Year of Assessment | Anticipated Replacement Date | Estimated Cost (Rounded) | Martinez yes? | Year Built | Year of Most Recent Renovation | Facilities Committee Planned Replacement Date | Revised Master Plan Itemized List Breakdown |  | 2024-02-08 | 769240
X | X | X | X |  | X | X | X | X | X
AA | Classrooms 6-8 | Classrooms 6 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
AA | Classrooms 6-8 | Classrooms 7 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
AA | Classrooms 6-8 | Classrooms 8 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
B | Classrooms 10-13 | Classrooms 10 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
B | Classrooms 10-13 | Classrooms 11 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
B | Classrooms 10-13 | Classrooms 12 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
B | Classrooms 10-13 | Classrooms 13 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
BB | Administration | Lobby | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
BB | Administration | Lobby | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
C | Transitional Kindergarten | Classroom 2 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
C | Transitional Kindergarten | Classroom 2 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
CC | Support Services | Classroom 38 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
CC | Support Services | 39 Wildcat's Room | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
CC | Support Services | 39 Wildcat's Room | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
D | Classrooms Kindergarten | Classroom 3 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
D | Classrooms Kindergarten | Classroom 4 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
D | Classrooms Kindergarten | Classroom 5 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
DD | Music Classrooms 36 &37 | Classroom 36 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
DD | Music Classrooms 36 &37 | Classroom 37 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
E | Classrooms 15-19 | Classrooms 15 | HVAC Units | New split unit 11/7/16 | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 19231 | Martinez 24+
E | Classrooms 15-19 | Classrooms 16 | HVAC Units | Room 16 New heat pump condenser installed 6/17/22. | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 19231 | Martinez 24+
E | Classrooms 15-19 | Classrooms 17 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
E | Classrooms 15-19 | Classrooms 18 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
E | Classrooms 15-19 | Classrooms 19 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
E | Classrooms 15-19 | MDF Room | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
F | Classrooms 26-29 | Classrooms 26 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
F | Classrooms 26-29 | Classrooms 27 | HVAC Units | Installed 6/23/17 | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 19231
F | Classrooms 26-29 | Classrooms 28 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
F | Classrooms 26-29 | Classrooms 29 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
FF | Classrooms 9, 14, & 20 | Classrooms 9 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
FF | Classrooms 9, 14, & 20 | Classrooms 14 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
FF | Classrooms 9, 14, & 20 | Classrooms 20 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
G | Community Gym | Office | HVAC Units | PTAC Wall Heat Pump 1/27/20 | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 19231 | Martinez 24+
G | Community Gym | Office | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
G | Community Gym | Office | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
GG | Classrooms 21 & 22 | Classrooms 21 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
GG | Classrooms 21 & 22 | Classrooms 22 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
M | Classrooms 23 - 25 | Classroom 23 - Science | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
M | Classrooms 23 - 25 | Classroom 24 - Science | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
M | Classrooms 23 - 25 | Classroom 25 - Art | HVAC Units | Installed 2/26/18 | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 19231
S | Classrooms 30 - 32 | Classrooms 30 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
S | Classrooms 30 - 32 | Classrooms 31 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
T | Classrooms 33 & 34 | Classrooms 33 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
T | Classrooms 33 & 34 | Classrooms 34 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231 | Martinez 24+
U | Classroom 35 | Classrooms 35 | HVAC Units |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19231
SELMAN | Selman Multi-Purpose Building | Multi-Purpose | HVAC Units |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 |  | Installed in '16
SELMAN | Selman Multi-Purpose Building | Principal Office | HVAC Units |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 |  | Installed in '16
SELMAN | Selman Multi-Purpose Building | Kitchen | HVAC Units |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 |  | Installed in '16
P | Pre-School | Pre-School | HVAC Units |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 |  | Installed in '16
P | Pre-School | Pre-School | HVAC Units |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 |  | Installed in '16
Improve Safety with Security Cameras and exterior lighting |  |  |  | Filtered Total: |  |  |  |  | 461460 |  |  |  |  | Original Master Plan Itemized list Breakdown |  | 2023-11-28 | 500000
Building ID | Building Description | Room Description | Item | Notes (Second Assessment) | Assessed Condition | Remaining Years At Time of Assessment | Year of Assessment | Anticipated Replacement Date | Estimated Cost (Rounded) | Martinez yes? | Year Built | Year of Most Recent Renovation | Facilities Committee Planned Replacement Date | Revised Master Plan Itemized List Breakdown |  | 2024-02-08 | 461460
X | X | X | X |  | X | X | X | X | X |  |  |  |  | Security Cameras throughout |  |  | 800000
AA | Classrooms 6-8 | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 21580 |  |  |  |  | Fire alarm replacement |  |  | 1100000
B | Classrooms 10-13 | Exterior | Exterior Lighting | Plumbing chase door is wood and wood frame | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 24660
BB | Administration | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 30830
C | Transitional Kindergarten | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032
CC | Support Services | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 33910
D | Classrooms Kindergarten | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032
DD | Music Classrooms 36 &37 | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 15250
E | Classrooms 15-19 | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 24660
F | Classrooms 26-29 | Exterior | Exterior Lighting | MARTINEZ IS Asking for all new lighting. LED. | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 27750
FF | Classrooms 9, 14, & 20 | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 27750
G | Community Gym | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 55500
GG | Classrooms 21 & 22 | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 27750
H | Library | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 15420
M | Classrooms 23 - 25 | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 43160
S | Classrooms 30 - 32 | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 21580
T | Classrooms 33 & 34 | Exterior | Exterior Lighting | Exterior light standard works but they can't get parts and he is salvaging for repair. | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 32330
U | Classroom 35 | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 12330
SELMAN | Selman Multi-Purpose Building | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 21580
P | Pre-School | Exterior | Exterior Lighting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 25420
Exterior Building Upgrades |  |  |  | Filtered Total: |  |  |  |  | 3054290 |  |  |  |  | Original Master Plan Itemized list Breakdown |  | 2023-11-28 | 3195000
Building ID | Building Description | Room Description | Item | Notes (Second Assessment) | Assessed Condition | Remaining Years At Time of Assessment | Year of Assessment | Anticipated Replacement Date | Estimated Cost (Rounded) | Martinez yes? | Year Built | Year of Most Recent Renovation | Facilities Committee Planned Replacement Date | Revised Master Plan Itemized List Breakdown |  | 2024-02-08 | 3054290
X | X | X | X |  | X | X | X | X | X | [5 empty] | Conference Room Skylights |  | 115000
SITE | Site | Main Hardcourt | AC Paving |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 365340
SITE | Site | Kindergarten Hardcourt | AC Paving |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 296430
SITE | Site | Parking Lots | AC Paving |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 676490
SITE | Site | Exterior | Drinking Fountains |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 147450 | yes
AA | Classrooms 6-8 | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 47340
AA | Classrooms 6-8 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 650
AA | Classrooms 6-8 | Exterior | Exterior Door | AND WOOD FRAMES | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 56390
AA | Classrooms 6-8 | Classrooms 6 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9250
AA | Classrooms 6-8 | Classrooms 7 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9250
AA | Classrooms 6-8 | Classrooms 8 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9250
B | Classrooms 10-13 | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 44780
B | Classrooms 10-13 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
BB | Administration | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 55330
BB | Administration | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
BB | Administration | Exterior | Exterior Door | Wood doors in wood frames | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 54120 | yes
BB | Administration | Lobby | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 161800
C | Transitional Kindergarten | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
C | Transitional Kindergarten | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032
C | Transitional Kindergarten | Exterior | Exterior Door | Hm doors in wood frames | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
CC | Support Services | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 29940
CC | Support Services | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
CC | Support Services | Exterior | Exterior Door | Wood frames too | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 74120
CC | Support Services | Classroom 38 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 64860
D | Classrooms Kindergarten | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032
D | Classrooms Kindergarten | Exterior | Windows |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Exterior | Glazing |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Exterior | Exterior Door | HM doors wood frames | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
DD | Music Classrooms 36 &37 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
DD | Music Classrooms 36 &37 | Exterior | Exterior Door | Wood doors and frames. | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 38590 | yes
DD | Music Classrooms 36 &37 | Classroom 36 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 8800
DD | Music Classrooms 36 &37 | Classroom 37 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 11110
DD | Music Classrooms 36 &37 | Practice Room 1 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
DD | Music Classrooms 36 &37 | Practice Room 2 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4420
DD | Music Classrooms 36 &37 | Practice Room 3 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
E | Classrooms 15-19 | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 39960
E | Classrooms 15-19 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
F | Classrooms 26-29 | Exterior | Exterior Wall Finish | Paint all exteriors typical all buildings per MArtinez. | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 39350
F | Classrooms 26-29 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
F | Classrooms 26-29 | Exterior | Fascia Material |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 45360
F | Classrooms 26-29 | Exterior | Windows | One upper window wont close. Martinez wants all exterior windows done on this building. MOST ARE IN GOOD SHAPE. | 00 - Critical - Replace Now | 0 | 2022 | Now | 121970
FF | Classrooms 9, 14, & 20 | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 51630
FF | Classrooms 9, 14, & 20 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
FF | Classrooms 9, 14, & 20 | Classrooms 9 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 8300
FF | Classrooms 9, 14, & 20 | Classrooms 14 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 10050
FF | Classrooms 9, 14, & 20 | Classrooms 20 | Window Coverings |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 16140
G | Community Gym | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 67400
G | Community Gym | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 550
G | Community Gym | Exterior | Exterior Roll-up Doors |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 9200
GG | Classrooms 21 & 22 | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 25940
GG | Classrooms 21 & 22 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
GG | Classrooms 21 & 22 | Exterior | Exterior Door | Exterior doors are wood doors in HM frames. Need replacement | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 10880 | yes
GG | Classrooms 21 & 22 | Classrooms 21 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 16140
GG | Classrooms 21 & 22 | Classrooms 22 | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9200
H | Library | Exterior | Exterior Wall Finish |  | 00 - Critical - Replace Now | 0 | 2022 | Now | 34210
H | Library | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
H | Library | Exterior | Windows |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 75120
H | Library | Exterior | Glazing |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 37460
H | Library | Exterior | Exterior Door | Wood doors and frames | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 33200
M | Classrooms 23 - 25 | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 56420
M | Classrooms 23 - 25 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
M | Classrooms 23 - 25 | Exterior | Fascia Material |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 24990
M | Classrooms 23 - 25 | Exterior | Exterior Door | all south doors are wood. Should replace with HM and HM frame. | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 50780 | yes
M | Classrooms 23 - 25 | Classroom 23 - Science | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 27330
M | Classrooms 23 - 25 | Classroom 24 - Science | Window Coverings |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 13250
S | Classrooms 30 - 32 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
T | Classrooms 33 & 34 | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9290
T | Classrooms 33 & 34 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 550
U | Classroom 35 | Exterior | Exterior Wall Finish |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9650
U | Classroom 35 | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 550
SELMAN | Selman Multi-Purpose Building | Exterior | Exterior Wall Finish | Painting in areas and around doors | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 31640
SELMAN | Selman Multi-Purpose Building | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 1870
P | Pre-School | Exterior | Downspouts |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 350
Modernize Classrooms |  |  |  | Filtered Total: |  |  |  |  | 2285390 |  |  |  |  | Original Master Plan Itemized list Breakdown |  | 2023-11-28 | 2515000
Building ID | Building Description | Room Description | Item | Notes (Second Assessment) | Assessed Condition | Remaining Years At Time of Assessment | Year of Assessment | Anticipated Replacement Date | Estimated Cost (Rounded) | Martinez yes? | Year Built | Year of Most Recent Renovation | Facilities Committee Planned Replacement Date | Revised Master Plan Itemized List Breakdown |  | 2024-02-08 | 2285390
X | X | X | X |  | X | X | X | X | X |  |  |  |  | Repair/Replace classrooms for current educational standards |  |  | 760000
AA | Classrooms 6-8 | Boy's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
AA | Classrooms 6-8 | Girl's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
AA | Classrooms 6-8 | PE Storage / IDF | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
AA | Classrooms 6-8 | Classrooms 6 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
AA | Classrooms 6-8 | Classrooms 6 | Wall Finish - Vinyl Covered Tackboard |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 89500
AA | Classrooms 6-8 | Classrooms 6 | Carpet Replacement |  | 00 - Critical - Replace Now | 0 | 2022 | Now | 35220 |  |  | 2023
AA | Classrooms 6-8 | Classrooms 6 | Linoleum Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 2500 |  |  | 2023
AA | Classrooms 6-8 | Classrooms 6 | Counter Tops |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 2500 | Summer 24 |  |  | Summer 2024
AA | Classrooms 6-8 | Classrooms 7 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
AA | Classrooms 6-8 | Classrooms 7 | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 35220 | Summer 24 |  |  | Summer 2024
AA | Classrooms 6-8 | Classrooms 7 | Linoleum Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 1860
AA | Classrooms 6-8 | Classrooms 7 | Counter Tops | Cabinet damage | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 1810 | Summer 24 |  |  | Summer 2024
AA | Classrooms 6-8 | Classrooms 8 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
AA | Classrooms 6-8 | Classrooms 8 | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 25220 | Summer 24 |  |  | Summer 2024
AA | Classrooms 6-8 | Classrooms 8 | Linoleum Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 1130
AA | Classrooms 6-8 | Classrooms 8 | Counter Tops |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 6340 | Summer 24 |  |  | Summer 2024
B | Classrooms 10-13 | Men's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3000
B | Classrooms 10-13 | Men's Toilet Room | Ceiling |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3520
B | Classrooms 10-13 | Men's Toilet Room | Counter Tops | [5 empty] | 2500 | Summer 24 |  |  | Summer 2024
B | Classrooms 10-13 | Women's Toilet Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
B | Classrooms 10-13 | Women's Toilet Room | Counter Tops | [5 empty] | 2500 | Summer 24 |  |  | Summer 2024
B | Classrooms 10-13 | Boy's Toilet Room | Interior Painting |  | 00 - Critical - Replace Now | 0 | 2022 | Now | 2350
B | Classrooms 10-13 | Boy's Toilet Room | Partitions |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 22720
B | Classrooms 10-13 | Girl's Toilet Room | Interior Painting |  | 00 - Critical - Replace Now | 0 | 2022 | Now | 2350
B | Classrooms 10-13 | Girl's Toilet Room | Partitions |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 31810
B | Classrooms 10-13 | Electrical Room | Interior Painting |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 1410
B | Classrooms 10-13 | Classrooms 10 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3820
B | Classrooms 10-13 | Classrooms 10 | VCT Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 12400
B | Classrooms 10-13 | Classrooms 10 | Counter Tops | Bad counter | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 1920 | Summer 24 |  |  | Summer 2024
B | Classrooms 10-13 | Classrooms 11 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3820
B | Classrooms 10-13 | Classrooms 11 | VCT Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 12400
B | Classrooms 10-13 | Classrooms 11 | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 1920 | Summer 24 |  |  | Summer 2024
B | Classrooms 10-13 | Classrooms 12 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3820
B | Classrooms 10-13 | Classrooms 12 | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 12400
B | Classrooms 10-13 | Classrooms 12 | Counter Tops | Old counter style | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 1920 | Summer 24 |  |  | Summer 2024
B | Classrooms 10-13 | Classrooms 13 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3820
B | Classrooms 10-13 | Classrooms 13 | VCT Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 12400
B | Classrooms 10-13 | Classrooms 13 | Casework | Some cabinet repair needed. | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 7900
B | Classrooms 10-13 | Classrooms 13 | Counter Tops | Old counter type. | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 1920 | Summer 24 |  |  | Summer 2024
BB | Administration | Lobby | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4110
BB | Administration | Lobby | Linoleum Replacement | Now wood flooring | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 19570
BB | Administration | Lobby | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 22240
BB | Administration | Hallways | Interior Painting | Lobby casework has minor bump damage. | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 8920
BB | Administration | Hallways | Linoleum Replacement | Now wood flooring | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 8220
BB | Administration | Hallways | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
BB | Administration | Offices (Admin) | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 25820
BB | Administration | Offices (Admin) | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 28520 | yes |  |  | 2024
BB | Administration | Conference Rooms | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 13840
BB | Administration | Conference Rooms | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 11730 | yes |  |  | 2024
BB | Administration | Electrical Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 25100
BB | Administration | Electrical Room | Linoleum Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 4500
BB | Administration | Nurse's Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 19340
BB | Administration | Nurse's Room | Linoleum Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 4500
BB | Administration | Nurse's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
BB | Administration | Men's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3040
BB | Administration | Women's Toilet Room | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 24810
BB | Administration | Women's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
BB | Administration | Workroom | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4250
BB | Administration | Workroom | Linoleum Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 25280 | Summer 24 |  |  | Summer 2024
BB | Administration | Workroom | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500 | Summer 24 |  |  | Summer 2024
BB | Administration | Staff Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 10560
BB | Administration | Staff Room | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 17750 | Summer 24 |  |  | Summer 2024
BB | Administration | Staff Room | Casework | Casework has minor PLam damage | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19740
BB | Administration | Staff Room | Counter Tops |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 19500 | Summer 24 |  |  | Summer 2024
C | Transitional Kindergarten | Classroom 2 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
C | Transitional Kindergarten | Classroom 2 | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
C | Transitional Kindergarten | Classroom 2 | Carpet Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
C | Transitional Kindergarten | Student Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
C | Transitional Kindergarten | Office / Workroom | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
C | Transitional Kindergarten | Office / Workroom | Linoleum Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032
C | Transitional Kindergarten | Electrical Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
CC | Support Services | Classroom 38 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 1340
CC | Support Services | Classroom 38 | Linoleum Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 1500
CC | Support Services | Classroom 38 | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 16070 | Summer 24 |  |  | Summer 2024
CC | Support Services | Classroom 38 | Counter Tops | Old Style | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 1520 | yes
CC | Support Services | Classroom 38A | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 6850
CC | Support Services | Classroom 38A | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3170 | yes
CC | Support Services | Classroom 38B | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
CC | Support Services | Classroom 38B | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
CC | Support Services | Classroom 38B | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2570 | yes
CC | Support Services | Classroom 38B | Counter Tops | Old style. Some delaminating. | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 2500 | Summer 24 |  |  | Summer 2024
CC | Support Services | Classroom 38C | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
CC | Support Services | Classroom 38C | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
CC | Support Services | Classroom 38C | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2570 | yes
CC | Support Services | Classroom 38D | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
CC | Support Services | Classroom 38D | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
CC | Support Services | Classroom 38D | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 7690 | yes
CC | Support Services | Classroom 38E | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
CC | Support Services | Classroom 38E | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
CC | Support Services | Classroom 38E | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 5570 | yes
CC | Support Services | Classroom 38F | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
CC | Support Services | Classroom 38F | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
CC | Support Services | Classroom 38F | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5570 | yes
CC | Support Services | Foundation Office (39c) | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4230
CC | Support Services | Foundation Office (39c) | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9410 | yes
CC | Support Services | Classroom 39B - Speech | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
CC | Support Services | Classroom 39B - Speech | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
CC | Support Services | Classroom 39B - Speech | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3100 | yes
CC | Support Services | Classroom 39B - Speech | Counter Tops | Old Style | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 7980
CC | Support Services | 39A - Mena's Office | Wall Finish - Vinyl Covered Tackboard | Hole patching | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 39460
CC | Support Services | 39A - Mena's Office | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
CC | Support Services | 39A - Mena's Office | Linoleum Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2000
CC | Support Services | 39A - Mena's Office | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2860
CC | Support Services | 39A - Mena's Office | Counter Tops | Old Style | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 7980
CC | Support Services | 39 Wildcat's Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4730
CC | Support Services | 39 Wildcat's Room | Linoleum Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3500 | Summer 25 |  |  | Summer 2025
CC | Support Services | 39 Wildcat's Room | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 18600 | Summer 25 |  |  | Summer 2025
CC | Support Services | 39 Wildcat's Room | Counter Tops | Old Style | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 18250
CC | Support Services | 39 Wildcat's Room | Appliances |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 15200
D | Classrooms Kindergarten | Classroom 3 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Classroom 3 | Linoleum Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032
D | Classrooms Kindergarten | Classroom 3 | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Classroom 3 | Accordion Door |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032
D | Classrooms Kindergarten | Classroom 4 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Classroom 4 | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Classroom 4 | Carpet Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
D | Classrooms Kindergarten | Classroom 4 | Casework | Cabinets need some work | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Classroom 4 | Accordion Door |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032
D | Classrooms Kindergarten | Classroom 5 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Classroom 5 | Linoleum Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024
D | Classrooms Kindergarten | Classroom 5 | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Girl's Toilet Room | Tile - Ceramic |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Girl's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Boy's Toilet Room | Tile - Ceramic |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Boy's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Custodial Room | Mop sink |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032
D | Classrooms Kindergarten | Custodial Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
D | Classrooms Kindergarten | Electrical Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027
DD | Music Classrooms 36 &37 | Classroom 36 | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 6230
DD | Music Classrooms 36 &37 | Classroom 36 | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 8690 | Summer 25 |  |  | Summer 2025
DD | Music Classrooms 36 &37 | Classroom 36 | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 19500 | Summer 25 |  |  | Summer 2025
DD | Music Classrooms 36 &37 | Classroom 37 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
DD | Music Classrooms 36 &37 | Classroom 37 | Linoleum Replacement | Transition seperation | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500 | Summer 25 |  |  | Summer 2025
DD | Music Classrooms 36 &37 | Classroom 37 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 19940 | Summer 25 |  |  | Summer 2025
DD | Music Classrooms 36 &37 | Classroom 37 | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9430 | Summer 24 |  |  | Summer 2024
DD | Music Classrooms 36 &37 | Office | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
DD | Music Classrooms 36 &37 | Office | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2470 | Summer 25 |  |  | Summer 2025
DD | Music Classrooms 36 &37 | Storage | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
DD | Music Classrooms 36 &37 | Storage | Linoleum Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5500 | Summer 25 |  |  | Summer 2025
DD | Music Classrooms 36 &37 | Practice Room 1 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4240
DD | Music Classrooms 36 &37 | Practice Room 1 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 4430 | Summer 25 |  |  | Summer 2025
DD | Music Classrooms 36 &37 | Practice Room 2 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5230
DD | Music Classrooms 36 &37 | Practice Room 2 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3900 | Summer 25 |  |  | Summer 2025
DD | Music Classrooms 36 &37 | Practice Room 3 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4240
DD | Music Classrooms 36 &37 | Practice Room 3 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 5430 | Summer 25 |  |  | Summer 2025
E | Classrooms 15-19 | Classrooms 15 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3820
E | Classrooms 15-19 | Classrooms 15 | Counter Tops | Good shape. Old type. Some damage. | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5870
E | Classrooms 15-19 | Classrooms 16 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3820
E | Classrooms 15-19 | Classrooms 16 | VCT Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 18400
E | Classrooms 15-19 | Classrooms 16 | Counter Tops | Old style | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 2940 | yes
E | Classrooms 15-19 | Classrooms 17 | Interior Painting | Add in Room 18. Part of this building but I don't see it listed. CcxNewer vainly flooring. No casework or sink. All IT stuff. Ceiling good, paint good, acoustical good. | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3820
E | Classrooms 15-19 | Classrooms 17 | VCT Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 12400
E | Classrooms 15-19 | Classrooms 17 | Counter Tops | Old type | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3300
E | Classrooms 15-19 | Classrooms 18 | Interior Painting | Add in Room 18. Part of this building but I don't see it listed. CcxNewer vainly flooring. No casework or sink. All IT stuff. Ceiling good, paint good, acoustical good. | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2200
E | Classrooms 15-19 | Classrooms 18 | VCT Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 11910
E | Classrooms 15-19 | Classrooms 19 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2890
E | Classrooms 15-19 | Electrical Room | Interior Painting | Locked out | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5720
E | Classrooms 15-19 | Electrical Room | Ceiling | Locked out | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3510
E | Classrooms 15-19 | MDF Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 6800
E | Classrooms 15-19 | Storage | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3060
F | Classrooms 26-29 | Classrooms 26 | Interior Painting | Good shape. Mostly all tack panel in 29-29 | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3760
F | Classrooms 26-29 | Classrooms 26 | Carpet Replacement | Stained | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 14780 | yes
F | Classrooms 26-29 | Classrooms 26 | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3990
F | Classrooms 26-29 | Classrooms 26 | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
F | Classrooms 26-29 | Classrooms 27 | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3760
F | Classrooms 26-29 | Classrooms 27 | Carpet Replacement | Stains, one snag | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 14780 | yes
F | Classrooms 26-29 | Classrooms 27 | VCT Replacement | 2 cracked tiles | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3300
F | Classrooms 26-29 | Classrooms 27 | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3300
F | Classrooms 26-29 | Classrooms 28 | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3760
F | Classrooms 26-29 | Classrooms 28 | Carpet Replacement | Stained | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 22000 | yes
F | Classrooms 26-29 | Classrooms 28 | VCT Replacement | 2 cracked tiles | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3300
F | Classrooms 26-29 | Classrooms 28 | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 17400
F | Classrooms 26-29 | Classrooms 29 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3760
F | Classrooms 26-29 | Classrooms 29 | Carpet Replacement | Bad stains | 00 - Critical - Replace Now | 0 | 2022 | Now | 15000 | yes
F | Classrooms 26-29 | Classrooms 29 | VCT Replacement | 1 cracked tile | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3300
F | Classrooms 26-29 | Classrooms 29 | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 17400
F | Classrooms 26-29 | Phone/Data Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
F | Classrooms 26-29 | Electrical Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
F | Classrooms 26-29 | Custodial Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
FF | Classrooms 9, 14, & 20 | Classrooms 9 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
FF | Classrooms 9, 14, & 20 | Classrooms 9 | Carpet Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 15000
FF | Classrooms 9, 14, & 20 | Classrooms 9 | VCT Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 2500
FF | Classrooms 9, 14, & 20 | Classrooms 9 | Counter Tops | Old bad counter at sink | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 5300 | yes
FF | Classrooms 9, 14, & 20 | Classrooms 14 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5020
FF | Classrooms 9, 14, & 20 | Classrooms 14 | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 25000 | Summer 25 |  |  | Summer 2025
FF | Classrooms 9, 14, & 20 | Classrooms 14 | VCT Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 2500 | Summer 24 |  |  | Summer 2024
FF | Classrooms 9, 14, & 20 | Classrooms 14 | Ceiling | 6 stained tiles and slight bowing | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 23000
FF | Classrooms 9, 14, & 20 | Classrooms 14 | Counter Tops | Old bad counter at sink | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3050 | Summer 24 |  |  | Summer 2024
FF | Classrooms 9, 14, & 20 | Classrooms 20 | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 4020
FF | Classrooms 9, 14, & 20 | Classrooms 20 | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 25000 | Summer 24 |  |  | Summer 2025
FF | Classrooms 9, 14, & 20 | Classrooms 20 | VCT Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 1500
FF | Classrooms 9, 14, & 20 | Classrooms 20 | Counter Tops | Old bad counter at sink | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 3490 | yes
FF | Classrooms 9, 14, & 20 | Mechanical Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3050
G | Community Gym | Gym | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 40000
G | Community Gym | Office | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
G | Community Gym | Office | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3130
G | Community Gym | PE Storage | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2800
G | Community Gym | Boy's Toilet Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
G | Community Gym | Girl's Toilet Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
G | Community Gym | Garage | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3430
G | Community Gym | Shower Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
G | Community Gym | Custodial Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
G | Community Gym | Storage | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 5490
G | Community Gym | Community Storage | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5500
GG | Classrooms 21 & 22 | Classrooms 21 | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2900
GG | Classrooms 21 & 22 | Classrooms 21 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 25000
GG | Classrooms 21 & 22 | Classrooms 21 | VCT Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 3300 | Summer 24 |  |  | Summer 2024
GG | Classrooms 21 & 22 | Classrooms 21 | Ceiling | 9 ceiling tiles need replacing. Grid isfine | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 32000
GG | Classrooms 21 & 22 | Classrooms 22 | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
GG | Classrooms 21 & 22 | Classrooms 22 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 20000
GG | Classrooms 21 & 22 | Classrooms 22 | VCT Replacement |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 2500
GG | Classrooms 21 & 22 | Storage/Data Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
GG | Classrooms 21 & 22 | Storage Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
H | Library | Library | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 9200
H | Library | Library | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 37000
H | Library | Library | Casework | Cabinets Casework needs refinish. | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 55000
H | Library | Computer Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
H | Library | Computer Room | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 4410
H | Library | Book Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
H | Library | Book Room | VCT Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
M | Classrooms 23 - 25 | Classroom 23 - Science | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 5460
M | Classrooms 23 - 25 | Classroom 23 - Science | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 25000
M | Classrooms 23 - 25 | Classroom 24 - Science | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 5460
M | Classrooms 23 - 25 | Classroom 24 - Science | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 14800
M | Classrooms 23 - 25 | Classroom 25 - Art | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5460
M | Classrooms 23 - 25 | Classroom 25 - Art | Counter Tops | coming off of walls | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 4710 | yes
M | Classrooms 23 - 25 | Mechanical Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
M | Classrooms 23 - 25 | Science Prep and Storage | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3370
M | Classrooms 23 - 25 | Science Prep and Storage | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 3660
M | Classrooms 23 - 25 | PE Storage | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3500
M | Classrooms 23 - 25 | Locker Breezeway | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5020
M | Classrooms 23 - 25 | Locker Breezeway | Lockers | At least paint | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 62000
M | Classrooms 23 - 25 | Boy's Toilet Room | Interior Painting |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 4660
M | Classrooms 23 - 25 | Girl's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4660
M | Classrooms 23 - 25 | Staff Toilet Room | VCT Replacement | Tile | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
M | Classrooms 23 - 25 | Staff Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
M | Classrooms 23 - 25 | Public Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
M | Classrooms 23 - 25 | Mechanical Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
M | Classrooms 23 - 25 | Art Office / Storage | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2790
M | Classrooms 23 - 25 | Kiln Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4610
S | Classrooms 30 - 32 | Classrooms 30 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4400
S | Classrooms 30 - 32 | Classrooms 30 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 17370
S | Classrooms 30 - 32 | Classrooms 30 | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 5200
S | Classrooms 30 - 32 | Classrooms 30 | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2120
S | Classrooms 30 - 32 | Classrooms 31 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4400
S | Classrooms 30 - 32 | Classrooms 31 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 27000
S | Classrooms 30 - 32 | Classrooms 31 | VCT Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 6230 | Summer 24 |  |  | Summer 2024
S | Classrooms 30 - 32 | Classrooms 31 | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 21750
S | Classrooms 30 - 32 | Classrooms 32 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4400
S | Classrooms 30 - 32 | Classrooms 32 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 22000
S | Classrooms 30 - 32 | Classrooms 32 | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
T | Classrooms 33 & 34 | Classrooms 33 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4400
T | Classrooms 33 & 34 | Classrooms 33 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 27500 | yes
T | Classrooms 33 & 34 | Classrooms 33 | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 4200
T | Classrooms 33 & 34 | Classrooms 33 | Counter Tops |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 29000
T | Classrooms 33 & 34 | Classrooms 34 | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 4400
T | Classrooms 33 & 34 | Classrooms 34 | Carpet Replacement |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 17370 | Summer 24 |  |  | Summer 2024
T | Classrooms 33 & 34 | Classrooms 34 | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 4200
U | Classroom 35 | Classrooms 35 | Wall Finish - Vinyl Covered Tackboard |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 5060
U | Classroom 35 | Classrooms 35 | Interior Painting |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 4400
U | Classroom 35 | Classrooms 35 | Carpet Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 37000 | Summer 24 |  |  | Summer 2024
U | Classroom 35 | Classrooms 35 | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2500
U | Classroom 35 | Classrooms 35 | Counter Tops |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 4500 | yes
SELMAN | Selman Multi-Purpose Building | Multi-Purpose | Interior Painting | Some spots | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 24500
SELMAN | Selman Multi-Purpose Building | Public Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 3200
SELMAN | Selman Multi-Purpose Building | Principal Office | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 2500
SELMAN | Selman Multi-Purpose Building | Principal Office | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 22000
SELMAN | Selman Multi-Purpose BuildingPrin | Principal Office | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 4300
SELMAN | Selman Multi-Purpose Building | Mechanical Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 2370
SELMAN | Selman Multi-Purpose Building | Boy's Toilet Room | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 6800
SELMAN | Selman Multi-Purpose Building | Girl's Toilet Room | Interior Painting |  | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 5310
SELMAN | Selman Multi-Purpose Building | Kitchen | Appliances | Fridge freezer and stove. | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 43000
P | Pre-School | Pre-School | Interior Painting |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 25000
P | Pre-School | Pre-School | VCT Replacement |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 32000
Athletic Upgrades |  |  |  | Filtered Total: |  |  |  |  | 3470000 |  |  |  |  | Original Master Plan Itemized list Breakdown |  | 2023-11-28 | 3470000
Building ID | Building Description | Room Description | Item | Notes (Second Assessment) | Assessed Condition | Remaining Years At Time of Assessment | Year of Assessment | Anticipated Replacement Date | Estimated Cost (Rounded) | Martinez yes? | Year Built | Year of Most Recent Renovation | Facilities Committee Planned Replacement Date | Revised Master Plan Itemized List Breakdown |  | 2024-02-08 | 3470000
X | X | X | X |  | X | X | X | X | X
SITE | Site | Soccer Field | Natural Turf | including drainage | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 350000
SITE | Site |  | Artificial Turf | including drainage | 05 - Recommend Improvement - 5 yrs | 5 | 2022 | 2027 | 1800000
SITE | Site | Basket Ball, Soccer | Athletic |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 115000
SITE | Site | Exterior | Shade Structures |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 500000
SITE | Site | Exterior | Play Structures | Not ADA compliant | 00 - Critical - Replace Now | 0 | 2022 | Now | 450000
SITE | Site | Exterior | Fencing |  | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 65000
SITE | Site | Exterior | Fencing | Some misc. repairs needed. | 02 - Necessary But Not Critical - 2 yrs | 2 | 2022 | 2024 | 45000
SITE | Site | Exterior | Fencing | Between parking lot and tennis courts repairs are needed for the wood retaining wall. | 00 - Critical - Replace Now | 0 | 2022 | Now | 80000
G | Community Gym | Gym | Bleachers |  | 10 - Recommend Improvement - 10 yrs | 10 | 2022 | 2032 | 65000
Note on B4: Tim Doane: Pulls from the District Master Tables - Campus Buildings Table
Note on F4: Tim Doane: See Drop Down List and Master Tables for "Condition" options
Note on G4: Tim Doane: 7-14-22 Changed this to be manually entered instead of based on the assessed condition column =VLOOKUP(O14,Remaining_Useful_Life,3,FALSE)
Note on B26: Tim Doane: Pulls from the District Master Tables - Campus Buildings Table
Note on F26: Tim Doane: See Drop Down List and Master Tables for "Condition" options
Note on G26: Tim Doane: 7-14-22 Changed this to be manually entered instead of based on the assessed condition column =VLOOKUP(O14,Remaining_Useful_Life,3,FALSE)
Note on B83: Tim Doane: Pulls from the District Master Tables - Campus Buildings Table
Note on F83: Tim Doane: See Drop Down List and Master Tables for "Condition" options
Note on G83: Tim Doane: 7-14-22 Changed this to be manually entered instead of based on the assessed condition column =VLOOKUP(O14,Remaining_Useful_Life,3,FALSE)
Note on B108: Tim Doane: Pulls from the District Master Tables - Campus Buildings Table
Note on F108: Tim Doane: See Drop Down List and Master Tables for "Condition" options
Note on G108: Tim Doane: 7-14-22 Changed this to be manually entered instead of based on the assessed condition column =VLOOKUP(O14,Remaining_Useful_Life,3,FALSE)
Note on B187: Tim Doane: Pulls from the District Master Tables - Campus Buildings Table
Note on F187: Tim Doane: See Drop Down List and Master Tables for "Condition" options
Note on G187: Tim Doane: 7-14-22 Changed this to be manually entered instead of based on the assessed condition column =VLOOKUP(O14,Remaining_Useful_Life,3,FALSE)
Note on B467: Tim Doane: Pulls from the District Master Tables - Campus Buildings Table
Note on F467: Tim Doane: See Drop Down List and Master Tables for "Condition" options
Note on G467: Tim Doane: 7-14-22 Changed this to be manually entered instead of based on the assessed condition column =VLOOKUP(O14,Remaining_Useful_Life,3,FALSE)

## Ext Build Up Pivot
Item | Glazing
Sum of Estimated | Column Labels
Row Labels | 05 - Recommend Improvement - 5 yrs | Grand Total
Classrooms Kindergarten
Library | 37460 | 37460
Grand Total | 37460 | 37460

## Carpet-VCT Analysis
0.22102 | 73025 | 330400
| 46621.9537 | 210940
| 46621.9537 | -0.36156

## Int Mod Pivot
Item | Counter Tops
Martinez yes? | Summer 24
Sum of Estimated | Column Labels
Row Labels | 02 - Necessary But Not Critical - 2 yrs | 05 - Recommend Improvement - 5 yrs | (blank) | Grand Total
Classroom 37 |  | 9430 |  | 9430 | Administration | 250310
Classroom 38B | 2500 |  |  | 2500 | Classrooms 10-13 | 194700
Classrooms 10 |  | 1920 |  | 1920 | Classrooms 23 - 25 | 162950
Classrooms 11 |  | 1920 |  | 1920 | Support Services | 161950
Classrooms 12 |  | 1920 |  | 1920 | Classrooms 6-8 | 139720
Classrooms 13 |  | 1920 |  | 1920 | Classrooms 30 - 32 | 117370
Classrooms 14 |  | 3050 |  | 3050 | Library | 113110
Classrooms 6 | 2500 |  |  | 2500 | Selman Multi-Purpose Building | 109680
Classrooms 7 | 1810 |  |  | 1810 | Classrooms 21 & 22 | 93200
Classrooms 8 | 6340 |  |  | 6340 | Classrooms 15-19 | 87520
Men's Toilet Room |  |  | 2500 | 2500 | Classrooms 26-29 | 77030
Staff Room | 19500 |  |  | 19500 | Community Gym | 72850
Women's Toilet Room |  |  | 2500 | 2500 | Classrooms 9, 14, & 20 | 62140
Workroom |  | 3500 |  | 3500 | Pre-School | 57000
Grand Total | 32650 | 23660 | 5000 | 61310 | Music Classrooms 36 &37 | 53560
[5 empty] | Classrooms 33 & 34 | 46200
[5 empty] | Classroom 35 | 11960
[5 empty] | Selman Multi-Purpose BuildingPrin | 4300

## R&R Renovations update
Repair and Replace (Renovation) | [5 empty] | From Pivot/Update w WES Expected numbers
|  |  | CPM Numbers |  |  | Martinez ID's | CPM Id'd |  | CPM Id'd
Athletic & Playground Repair & Replace |  |  | 3470000 |  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033
| Turf Field Replacement |  |  | 1800000 |  | CPM Id'd 2027: 1800000
| Shade Structures |  |  | 500000 |  | CPM Id'd 2027: 500000
| ADA Compliant Play Structures |  |  | 450000 |  | CPM Id'd 2027: 450000
| Natural Turf |  |  | 350000 |  | CPM Id'd 2027: 350000
| Fencing |  |  | 190000 |  | Martinez ID's 2024: 15000; CPM Id'd 2025: 15000; CPM Id'd 2026: 15000
| Other (Basketball/Soccer $115K/Bleachers $65k) |  |  | 180000
Scoreboard
Exterior Building Repair & Replace |  |  | 6426748
| Roofs |  |  | 1158240 |  | Martinez ID's 2024: 324270
| Exterior Lighting |  |  | 461460
| Paving |  |  | 1338260 | Main HC, K HC, parking lot
| Exterior Wall finish |  |  | 542880
| Window Covering |  |  | 385150
| Exterior Door |  |  | 318080 |  | Martinez ID's 2024: 159040; CPM Id'd 2025: 159040
| Windows |  |  | 197090 |  | Martinez ID's 2024: 121970; CPM Id'd 2027: 75120
| Drinking Fountains |  |  | 147450 |  | Martinez ID's 2024: 20000
| Fascia |  |  | 70000 |  | Martinez ID's 2024: 25000; CPM Id'd 2027: 45000
| Other |  |  | 125380
Interior Building Repair & Replace |  |  | 3045390
| Repair/Replace classrooms for current ed standards |  |  | 760000 | New Technology room?
| Flooring (Carpet/Linoleum/VCT) |  |  | 634970 |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
| Interior Painting |  |  | 545610 |  | CPM Id'd 2027: 396410
| Counter Tops |  |  | 310750 |  | Martinez ID's 2024: 61000; CPM Id'd 2026: 50000; CPM Id'd 2028: 50000; CPM Id'd 2031: 50000; CPM Id'd 2033: 50000
| Wall Finish - Vinyl Covered Tackboard |  |  | 127000 |  | CPM Id'd 2027: 200000
| Casework |  |  | 82640
| Partitions |  |  |  |  | CPM Id'd 2027: 54530
| Other |  |  | 236760
Technology Repairs and Replacement |  |  | 1900000
| Security Camera |  |  | 800000
| Fire Alarm Replacement |  |  | 1100000
Amphitheatre Repairs and Replacement |  |  | 2200000 | 2200000
Renovation Construction |  |  | 17042138 | 15011720
Construction Contingency (10%) |  |  | 1704213.8 | 1501172
Soft Costs (32%) |  |  | 5453484.16 | 4803750.4
|  | Sub Total: | 24199835.96 | 21316642.4
8% inflation first year |  |  | 1935986.8768 | 1705331.392
4% inflation second year |  |  | 967993.4384 | 852665.696
4% inflation third year |  |  | 967993.4384 | 852665.696
|  | Inflation Sub-Total: | 3871973.7536 | 3410662.784
|  | Total Repair and Replace Estimate: | 28071809.7136 | 24727305.184
Note on H8: Fence estimate behind 36 & 37
Note on I8: Fence estimate behind 36 & 37
Note on J8: Fence estimate behind 36 & 37

## Ext Pivot
R&R Renovations is linked to this
Row Labels | Sum of Estimated
AC Paving | 1338260 | 1338260
Downspouts | 8370 | 8370
Drinking Fountains | 147450 | 147450
Exterior Door | 318080 | 318080
Exterior Roll-up Doors | 9200 | 9200
Exterior Wall Finish | 542880 | 542880
Fascia Material | 70350 | 70350
Glazing | 37460 | 37460
Window Coverings | 385150 | 385150
Windows | 197090 | 197090
X | 0 | 0
(blank)
Grand Total | 3054290

## Technology Upgrades
Technology Upgrades
New PA/Bell System |  | 300000 | Per Harlin
Technology Upgrades to Classroom 15 |  | 450000
Sound System (Sellman?) |  | 80000 | Per Harlin
Technology Upgrades to Wilcats/Sellman |  | 70000 | Per Harlin
| Total: | 900000

## Int Pivot
Row Labels | Sum of Estimated
Accordion Door |  | Carpet Replacement | 634970
Appliances | 58200 | Interior Painting | 545610
Carpet Replacement | 634970 | Counter Tops | 310750
Casework | 82640 | VCT Replacement | 253220
Ceiling | 62030 | Wall Finish - Vinyl Covered Tackboard | 134020
Counter Tops | 315750 | Linoleum Replacement | 127000
Interior Painting | 545610 | Casework | 82640
Linoleum Replacement | 127000 | Ceiling | 62030
Lockers | 62000 | Lockers | 62000
Mop sink |  | Appliances | 58200
Partitions | 54530 | Partitions | 54530
Tile - Ceramic |  | Accordion Door
VCT Replacement | 253220 | Mop sink
Wall Finish - Vinyl Covered Tackboard | 134020 | Tile - Ceramic
X | 0
(blank)
Grand Total | 2329970

## HVAC Pivot
Martinez yes? | Martinez 24+
Row Labels | Sum of Estimated
02 - Necessary But Not Critical - 2 yrs | 307696 | 02 - Necessary But Not Critical - 2 yrs | 673085
10 - Recommend Improvement - 10 yrs | 57693 | 05 - Recommend Improvement - 5 yrs
Grand Total | 365389 | 10 - Recommend Improvement - 10 yrs | 96155
|  | X | 0
|  | Total | 769240 | 76924

## Creek Stabilization
Creek Embankment Stabilization
Construction Costs |  | 2000000
Construction Contingency (10%) |  | 200000
Soft Costs (32%) (Design fees, preconstruction planning services, consultants, the required Inspector of Record, DSA fees, and special inspections |  | 640000
as well as city and utility fees, Administrative Fees, Permits etc.) | Sub Total: | 2840000
8% inflation first year |  | 227200
0
0
| Inflation Sub-Total: | 227200
| Total Repair and Replace Estimate: | 3067200
Emergency Repairs - Creek Embankment Stabilization Project
Recent rain(s) have eroded the creek bank and expose the stitch pier stabilization system installed in 2012 and need immediate repairs.
Damages have caused subsidence adjacent to the soccer field and the existing field drainage system may have contributed in part to some of the erosion.
FEMA:
Initial meeting was held with FEMA, WESD, Consultants to review emergency repairs
FEMA awarded grant for emergency repairs
Project is currently in mitigation and is on-going
Investigation:
Borings were completed and Geotechnical Report finalized to determine design solution
Biologist assistance was also utilized to determine environmental impact mitigation
Currently working with civil engineering and biologist consultants for remediation scope.
Project Milestones: 2-3 years (Summer 2026)

## Replace Kinder.TK
Replace TK & Kindergarten Classrooms
Construction Costs | 8469 | SF
| 1000 | Per foot
8469000
Demolition Costs | 250000 | Existing Building Demo
Construction sub-total | 8719000
5% Contingency | 435950
32% Soft Cost | 2790080 | On Construction Cost
Sub-Total | 11945030
8% inflation first year | 955602.4 | Compounding costs
4% inflation second year | 516025.296 | Compounding costs
Inflation Sub-Total | 1471627.696
Total Repair and Replace Estimate | 13416657.696
Following are items reflecting why existing Kinder buildings are failing or need to be brought up to code:
1. Existing Kindergarten building doesn’t meet current minimum educational standards as required by the CDE.
The rooms do not meet the minimum 1350 square footage requirements.
2. Existing Kindergarten building doesn’t meet current accessibility requirements as required by the ADA
3. Existing building was originally constructed in 1969 and needs a lot of renovation modernization work.
We currently are estimating that the Kindergarten building requires about $1M in renovation work.
4. The existing building is not build with the same quality as the other building on campus and has been requiring higher maintenance than the other buildings.
If we added onto the existing Kindergarten building, DSA would require us to bring the building up to current code. This would cost all most as much as getting a new building that can be better designed and without the aging infrastructure.
5. Existing building is consuming valuable space that is need to add new TK rooms.
District doesn’t want to lose valuable and limited play space

## Amphiteatre Repairs and Replace
Amphitheatre Repairs and Replacement
Amphitheatre Upgrades to include ADA, new seating, sound and lighting | Total: | 2200000